## Sheet1
| Risk Statement |  | Probability | Damage Degree | Response Plan | Liable Person
| Situation | Consequence
1 | Requirement change after entering design or realization phase | Some pre-jobs need to be re-done and delay the work cycle | 20% | 8 | Do careful requirement analysis before doing the whole work. | Song Yiwen
2 | Coding time delay | Delay the whole project | 80% | 3 | Ask the team members to work overtime | Xie Zhihui
3 | Algorithm can't be realized | Chnge the way of design | 15% | 6 | Design carefully, considering the team's ability | Xie Zhihui
4 | Bugs not detected in the testing phase | Reduce the satisfaction of users | 100% | 2 | Repair the bugs as soon as possible | Wang Weizhe
5 | Problems with code management | Done works turn into nothing | 5% | 7 | Use code management platform | Chen Haoping
6 | Too many users than expected | Database overload and software can't run normally | 10% | 9 | If the situation occurs, enlarge the database as soon as possible | Jiang Huangfei